## Slide 1: Monthly Stakeholder Update Utilities Master Plan
March 28, 2023

## Slide 2
Status
Current Tasks
Upcoming Tasks
Schedule
Action Items
Phase 1: Assess existing utility systems to meet current levels of services
  Engage utilities to capture and compile existing data
  Field investigate critical features and attributes
  Evaluate risk for current operations
  Identify operational/maintenance/capital options
  Existing conditions report for review
STATUS

## Slide 3
Status
Current Tasks
Upcoming Tasks
Schedule
Action Items
  Ongoing field investigation and data collection
  Website content updated – dynamic site
  BOV Subcommittee UMP review
  CAC committee update
PREVIOUS ACTION ITEMS

## Slide 4
PROGRESS DASHBOARD

## Slide 5
FIELD INVESTIGATION SCHEDULE
Status
Current Tasks
Upcoming Tasks
Schedule
Action Items

## Slide 6
Continue utility field investigations
Coordinate VT GIS app for Thermal Distribution systems
VT GIS continued support of utility field investigations
2047 Master Plan Review workshop scheduled for 5/2/23 at The Inn at Virginia Tech
UPCOMING TASKS
Status
Current Tasks
Upcoming Tasks
Schedule
Action Items

## Slide 7
  UMP Monthly Stakeholder meeting on 4/25/2023
  Field Investigations weekly stakeholder reminder
  Schedule 30% Review Workshop to review Existing Conditions Report with stakeholders
  Schedule CAC Workshops on Decarbonizing, Air Emissions, and Measures of Success
ACTION ITEMS
Status
Current Tasks
Upcoming Tasks
Schedule
Action Items